## WBS & Gantt Chart
19 MJ: AI CAREER DEVELOPMENT & HIRING PLATFORM — WBS & GANTT CHART
Timeline: 30 Mar 2026 - 7 Jun 2026 (70 hari) ¦ Target: 55-63 hari ¦ Framework: Hybrid
WBS ID | Task / Deliverable | PIC | Start Date | End Date | Duration | Notes | W1 | W2 | W3 | W4 | W5 | W6-10
1 | PROJECT MANAGEMENT | Johanes | 30 Mar 2026 | 7 Jun 2026 | 70 | Continuous | ■ | ■ | ■ | ■ | ■ | ■
1.1 | Weekly progress monitoring | Johanes | 30 Mar 2026 | 7 Jun 2026 | 70 | Sprint reviews | ■ | ■ | ■ | ■ | ■ | ■
1.2 | Sprint planning & review | Johanes | 6 Apr 2026 | 7 Jun 2026 | 63 | Each sprint |  | ■ | ■ | ■ | ■ | ■
1.3 | Risk management | Johanes | 30 Mar 2026 | 7 Jun 2026 | 70 | Continuous | ■ | ■ | ■ | ■ | ■ | ■
2 | REQUIREMENT ANALYSIS & PREP | Team | 30 Mar 2026 | 5 Apr 2026 | 7 | Waterfall phase | ■
2.1 | Kickoff meeting | All | 30 Mar 2026 | 30 Mar 2026 | 1 | Project start | ■
2.2 | Review PRD/SKPL | Johanes+Team | 30 Mar 2026 | 1 Apr 2026 | 3 | Finalize requirements | ■
2.3 | Define system scope | Johanes | 1 Apr 2026 | 2 Apr 2026 | 2 | MVP boundaries | ■
2.4 | Tech architecture | Kevin+Dzaky | 3 Apr 2026 | 4 Apr 2026 | 2 | Hybrid AI design | ■
2.5 | Database schema (ERD) | Kevin+Dzaky | 3 Apr 2026 | 4 Apr 2026 | 2 | PostgreSQL | ■
2.6 | API contract design | Kevin+Dzaky | 4 Apr 2026 | 5 Apr 2026 | 2 | REST API spec | ■
2.7 | Infrastructure setup | Johanes+Kevin | 4 Apr 2026 | 5 Apr 2026 | 2 | Docker, Git | ■
2.8 | Lo-fi wireframe | Arrayyan | 4 Apr 2026 | 5 Apr 2026 | 2 | All pages | ■
2.9 | Final approval | Johanes | 5 Apr 2026 | 5 Apr 2026 | 1 | Sign-off | ■
⚠️ WBS ID 3+ (Development) menggunakan Agile Sprint. Lihat sheet "Sprint Board".

## Summary Dashboard
PROJECT SUMMARY DASHBOARD
Epic | Stories | Total SP | Must Have | Should Have | Could Have
Auth & User Management | 4 | 12 | 4 | 0 | 0
Candidate Profile | 2 | 10 | 2 | 0 | 0
CV Management | 3 | 16 | 3 | 0 | 0
Career Planner | 1 | 8 | 1 | 0 | 0
Interview Practice | 4 | 26 | 4 | 0 | 0
Job Management | 3 | 13 | 3 | 0 | 0
Recruiter Dashboard | 3 | 16 | 3 | 0 | 0
Infrastructure | 6 | 19 | 6 | 0 | 0
Testing & QA | 7 | 31 | 6 | 1 | 0
Documentation | 5 | 16 | 5 | 0 | 0
TOTAL | 38 | 167 | 37 | 1 | 0

## Sprint Board
SPRINT BOARD — 19 MJ Platform ¦ Sprint 1-5 Complete
Prep (19 SP) ¦ Sprint 1 (27 SP) ¦ Sprint 2 (24 SP) ¦ Sprint 3 (42 SP) ¦ Sprint 4 (29 SP) ¦ Sprint 5 (39 SP) ¦ Total: 180 SP
Sprint | ID | Epic | User Story (Summary) | Owner | SP (Story Points) | Priority | Status | Dependencies
Prep 30 Mar - 5 Apr (7 days) 19 SP | INFRA-01 | Infrastructure | Setup Git repository & branch strategy | Johanes | 2 | Must Have | Done | -
| INFRA-02 | Infrastructure | Setup Docker Compose (FE, BE, DB, AI) | Johanes+Kevin | 3 | Must Have | Done | INFRA-01
| INFRA-03 | Infrastructure | Setup PostgreSQL database & schema | Kevin+Dzaky | 3 | Must Have | Done | INFRA-02
| INFRA-04 | Infrastructure | Setup Local STT model | Kevin | 5 | Must Have | Done | INFRA-02
| INFRA-05 | Infrastructure | Setup LLM API (via Open Router & Google AI Studio) | Kevin | 3 | Must Have | Done | INFRA-02
| INFRA-06 | Infrastructure | Setup Vector DB (ChromaDB) | Kevin | 3 | Must Have | Done | INFRA-02
Sprint 1 6 - 19 Apr (14 days) 27 SP | US-001 | Auth & User Mgmt | Register Candidate | Arrayyan+Kevin | 3 | Must Have | Done | -
| US-002 | Auth & User Mgmt | Login Candidate | Arrayyan+Kevin | 3 | Must Have | Done | US-001
| US-003 | Auth & User Mgmt | Register Company | Arrayyan+Kevin | 3 | Must Have | Done | -
| US-004 | Auth & User Mgmt | Login Company | Arrayyan+Kevin | 3 | Must Have | Done | US-003
| US-005 | Candidate Profile | Create & update profile | Arrayyan+Dzaky | 5 | Must Have | Done | US-002
| US-006 | Candidate Profile | Add experience, education, skills | Arrayyan+Dzaky | 5 | Must Have | Done | US-005
| US-007 | Company Profile | Create company profile | Arrayyan+Dzaky | 5 | Must Have | Done | US-004
| QA-S1 | Testing & QA | Functional testing Sprint 1 (Auth+Profile) | Novian | 2 | Must Have | Done | US-007
Sprint 2 20 Apr - 3 May (14 days) 24 SP | US-008 | CV Management | Upload CV | Arrayyan+Kevin | 3 | Must Have | Done | US-005
| US-009 | CV Management | Extract text from CV | Kevin+Dzaky | 5 | Must Have | Done | US-008
| US-010 | CV Management | AI CV Review | Kevin+Arrayyan | 8 | Must Have | Done | US-009
| QA-S2 | Testing & QA | Functional testing Sprint 2 (CV) | Novian | 2 | Must Have | Done | US-010
Sprint 3 4 - 17 May (14 days) 42 SP | US-011 | Career Planner | Career path recommendation (AI roadmap) | Kevin+Arrayyan | 8 | Must Have | On Progress | US-005
| US-012 | Interview Practice | Interview practice (record answer) | Arrayyan+Kevin | 8 | Must Have | On Progress | US-005
| US-013 | Interview Practice | Auto-transcribe recording (STT) | Kevin | 8 | Must Have | Done | US-012
| US-014 | Interview Practice | Edit transcript | Arrayyan+Dzaky+Kevin | 5 | Must Have | Done | US-013
| US-015 | Interview Practice | AI evaluation (interview) | Kevin+Arrayyan | 5 | Must Have | On Progress | US-014
| QA-S3 | Testing & QA | Functional testing Sprint 3 (Career+Interview) | Novian | 3 | Must Have | To Do | US-015
Sprint 4 18 - 31 May (14 days) 29 SP | US-016 | Job Management | Create job posting | Arrayyan+Dzaky | 5 | Must Have | To Do | US-007
| US-017 | Job Management | Add screening questions | Dzaky | 3 | Must Have | To Do | US-016
| US-018 | Job Application | Apply to job | Arrayyan+Dzaky | 5 | Must Have | To Do | US-005
| US-019 | Job Application | Answer screening questions | All Team | 8 | Must Have | To Do | US-018,US-014
| QA-S4 | Testing & QA | Functional testing Sprint 4 (Job+Apply) | Novian | 3 | Must Have | To Do | US-019
Sprint 5 1 - 7 Jun (7 days) 39 SP | US-020 | Recruiter Dashboard | View candidate data | Arrayyan+Dzaky | 5 | Must Have | Planned | US-016
| US-021 | Recruiter Dashboard | View AI evaluation results | Arrayyan | 3 | Must Have | Planned | US-020
| US-022 | Recruiter Dashboard | Candidate recommendations (AI) | Kevin+Arrayyan | 8 | Must Have | Planned | US-020
| QA-08 | Testing & QA | AI accuracy testing | Novian+Kevin | 5 | Must Have | On Progress | -
| QA-09 | Testing & QA | Integration testing (E2E) | Novian+Team | 5 | Must Have | Planned | -
| QA-10 | Testing & QA | Performance testing | Novian | 3 | Must Have | Planned | -
| QA-11 | Testing & QA | Security testing (Pentest) | Johanes+Novian | 5 | Must Have | Planned | -
| DOC-01 | Documentation | API documentation (Swagger) | Kevin+Dzaky | 3 | Must Have | Done | -
| DOC-02 | Documentation | User manual (Candidate+Company) | Johanes+Arrayyan | 5 | Must Have | Planned | -

## Backlog Product
PRODUCT BACKLOG — 19 MJ: AI Career Development & Hiring Platform
v1.0 ¦ SK-F-001 to SK-F-021 ¦ 45 User Stories ¦ 180 Story Points ¦ Conservative-Moderate Velocity
ID | Epic | User Story | Acceptance Criteria | Priority | SP (Story Points) | Sprint | Owner | Status | Dependencies | SK-F | Type | Labels | Notes
US-001 | Auth & User Mgmt | Sebagai Candidate, saya ingin register akun agar dapat akses platform | • Form register (name, email, password) • Email validation • Password min 8 char • Account di DB • Redirect ke login | Must Have | 3 | Sprint 1 | Arrayyan+Kevin | Done | - | SK-F-001 | Feature | auth,candidate,fe,be | Include email verification (optional MVP)
US-002 | Auth & User Mgmt | Sebagai Candidate, saya ingin login agar dapat gunakan fitur platform | • Login form (email, password) • Authentication success • Session/token tersimpan • Redirect dashboard | Must Have | 3 | Sprint 1 | Arrayyan+Kevin | Done | US-001 | SK-F-002 | Feature | auth,candidate,fe,be | After login blank page OK (MVP)
US-003 | Auth & User Mgmt | Sebagai Company, saya ingin register akun agar dapat post lowongan | • Form register company (name, email, password) • Email validation • Account tersimpan • Redirect login | Must Have | 3 | Sprint 1 | Arrayyan+Kevin | Done | - | SK-F-015 | Feature | auth,company,fe,be
US-004 | Auth & User Mgmt | Sebagai Company, saya ingin login agar dapat manage lowongan | • Login form company • Authentication success • Session tersimpan • Redirect company dashboard | Must Have | 3 | Sprint 1 | Arrayyan+Kevin | Done | US-003 | SK-F-015 | Feature | auth,company,fe,be
US-005 | Candidate Profile | Sebagai Candidate, saya ingin create & update profile agar recruiter lihat background | • Form profile (summary, headline) • CRUD API works • Profile tersimpan • Profile page displays API data | Must Have | 5 | Sprint 2 | Arrayyan+Dzaky | On Progress | US-002 | SK-F-003 | Feature | profile,candidate,fe,be
US-006 | Candidate Profile | Sebagai Candidate, saya ingin add experience, education, skills agar profile lengkap | • Form add experience (company, role, duration) • Form add education (school, degree, year) • Form add skills • Data tersimpan & tampil | Must Have | 5 | Sprint 2 | Arrayyan+Dzaky | On Progress | US-005 | SK-F-004 | Feature | profile,candidate,fe,be
US-007 | Company Profile | Sebagai Company, saya ingin create company profile agar candidate tahu perusahaan | • Form company profile (name, industry, description, location) • CRUD API • Profile tersimpan & tampil | Must Have | 5 | Sprint 2 | Arrayyan+Dzaky | On Progress | US-004 | SK-F-016 | Feature | profile,company,fe,be
QA-S1 | Testing & QA | Functional testing Sprint 1 features (Auth & Profile) | • Test register/login Candidate+Company • Test profile CRUD • Pass rate ≥95% • Bugs documented | Must Have | 2 | Sprint 1 | Novian | Done | US-007 | - | Testing | qa,functional,sprint1 | Test auth & profile features
US-008 | CV Management | Sebagai Candidate, saya ingin upload CV agar AI analyze | • Upload form (PDF/DOCX) • File validation (max 5MB) • File tersimpan (cloud storage) • Metadata CV di DB | Must Have | 3 | Sprint 2 | Arrayyan+Kevin | On Progress | US-005 | SK-F-005 | Feature | cv,upload,fe,be | TBD: Cloud storage provider
US-009 | CV Management | Sebagai System, saya harus extract text dari CV agar AI process | • CV parsing (PDF/DOCX → text) • Text extraction accuracy ≥90% • Parsed text tersimpan di DB | Must Have | 5 | Sprint 2 | Kevin+Dzaky | On Progress | US-008 | SK-F-006 | Feature | cv,parsing,be | Use PyPDF2 or python-docx
US-010 | CV Management | Sebagai Candidate, saya ingin AI CV review agar tahu strengths & weaknesses | • AI review via LLM API • Output: score, strengths, weaknesses, suggestions • Response time ≤5s • Result tampil UI | Must Have | 8 | Sprint 2 | Kevin+Arrayyan | On Progress | US-009 | SK-F-007 | Feature | cv,ai,llm,fe,be | LLM: Qwen 3.6 via Open Router
QA-S2 | Testing & QA | Functional testing Sprint 2 features (CV Management) | • Test CV upload • Test CV parsing accuracy • Test AI review output • Pass rate ≥95% | Must Have | 2 | Sprint 2 | Novian | On Progress | US-010 | - | Testing | qa,functional,sprint2 | Test CV features + AI accuracy
US-011 | Career Planner | Sebagai Candidate, saya ingin career path recommendation agar tahu skill yang harus dipelajari | • Select target role • AI generate roadmap (skills, learning path, gap analysis) • Response ≤5s • Roadmap tampil UI | Must Have | 8 | Sprint 3 | Kevin+Arrayyan | Done | US-005 | SK-F-008 | Feature | career,ai,llm,fe,be | Prompt engineering for career roadmap
US-012 | Interview Practice | Sebagai Candidate, saya ingin practice interview agar lebih siap | • Select role/field • System generate question • Record audio/video answer • Media tersimpan | Must Have | 8 | Sprint 3 | Arrayyan+Kevin | On Progress | US-005 | SK-F-009 | Feature | interview,practice,fe,be | TBD: Media storage
US-013 | Interview Practice | Sebagai System, saya harus auto-transcribe recording agar jawaban dapat dianalisis | • Local STT model (Whisper.cpp/Vosk) • Audio extraction from video • Transcription accuracy ≥85% • Transcript tersimpan | Must Have | 8 | Sprint 3 | Kevin | Done | US-012 | SK-F-010 | Feature | interview,stt,ai,be | TBD: STT model (Whisper.cpp recommended)
US-014 | Interview Practice | Sebagai Candidate, saya ingin edit transcript agar kesalahan dapat diperbaiki | • Transcript editor UI • Edit & save functionality • Transcript final tersimpan • Transcript final = source of truth | Must Have | 5 | Sprint 3 | Arrayyan+Dzaky | Planned | US-013 | SK-F-011 | Feature | interview,transcript,fe,be
US-015 | Interview Practice | Sebagai Candidate, saya ingin AI evaluation agar tahu kualitas jawaban | • AI evaluate transcript final • Output: score, strengths, weaknesses, suggestions • Response ≤5s • Result tampil | Must Have | 5 | Sprint 3 | Kevin+Arrayyan | On Progress | US-014 | SK-F-012 | Feature | interview,ai,llm,fe,be | Prompt engineering for interview eval
QA-S3 | Testing & QA | Functional testing Sprint 3 features (Career + Interview) | • Test career planner output • Test interview recording • Test STT accuracy • Test transcript edit • Test AI eval • Pass ≥95% | Must Have | 3 | Sprint 3 | Novian | Planned | US-015 | - | Testing | qa,functional,sprint3 | Test career & interview features
US-016 | Job Management | Sebagai Company, saya ingin create job posting agar candidate dapat apply | • Form job posting (title, description, requirements, field) • CRUD API • Job tersimpan & published | Must Have | 5 | Sprint 4 | Arrayyan+Dzaky | Planned | US-007 | SK-F-017 | Feature | job,company,fe,be
US-017 | Job Management | Sebagai Company, saya ingin add screening questions agar filter candidate | • Form screening questions • Multiple questions per job • Questions tersimpan • Questions tampil saat apply | Must Have | 3 | Sprint 4 | Dzaky | Planned | US-016 | SK-F-018 | Feature | job,screening,be
US-018 | Job Application | Sebagai Candidate, saya ingin apply ke job agar dapat melamar | • Job list page • Job detail page • Apply button • Application tersimpan • Status application visible | Must Have | 5 | Sprint 4 | Arrayyan+Dzaky | Planned | US-005 | SK-F-013 | Feature | job,candidate,fe,be
US-019 | Job Application | Sebagai Candidate, saya ingin answer screening questions agar perusahaan evaluate | • View screening questions • Record answer (audio/video) • Auto-transcribe • Edit transcript • AI evaluate • Submit | Must Have | 8 | Sprint 4 | All Team | Planned | US-018,US-014 | SK-F-014 | Feature | screening,interview,fe,be,ai | Reuse interview practice flow
QA-S4 | Testing & QA | Functional testing Sprint 4 features (Job Management & Application) | • Test job posting • Test screening questions • Test job apply • Test screening answers • Pass ≥95% | Must Have | 3 | Sprint 4 | Novian | Planned | US-019 | - | Testing | qa,functional,sprint4 | Test job & application features
US-020 | Recruiter Dashboard | Sebagai Recruiter, saya ingin view candidate data agar evaluate applicants | • Dashboard view applicants per job • View profile, CV, transcript • Filter & sort candidates | Must Have | 5 | Sprint 5 | Arrayyan+Dzaky | Planned | US-016 | SK-F-019 | Feature | recruiter,dashboard,fe,be
US-021 | Recruiter Dashboard | Sebagai Recruiter, saya ingin view AI evaluation agar lihat analisa objektif | • View AI CV review score • View AI interview eval score • View AI screening eval score • View feedback details | Must Have | 3 | Sprint 5 | Arrayyan | Planned | US-020 | SK-F-020 | Feature | recruiter,ai,fe
US-022 | Recruiter Dashboard | Sebagai Recruiter, saya ingin candidate recommendations agar find best fit | • AI recommend candidates based on job requirements • Ranking by match score • Show reasoning | Must Have | 8 | Sprint 5 | Kevin+Arrayyan | Planned | US-020 | SK-F-021 | Feature | recruiter,ai,llm,fe,be | Simple similarity scoring MVP
INFRA-01 | Infrastructure | Setup Git repository & branch strategy | • Git repo created • Branch strategy documented (main, dev, feature/*) • README.md • .gitignore | Must Have | 2 | Prep | Johanes | Done | - | - | Chore | infra,setup,git | Week 1 - Preparation
INFRA-02 | Infrastructure | Setup Docker Compose (FE, BE, DB, AI) | • docker-compose.yml • All services running • Hot reload configured | Must Have | 3 | Prep | Johanes+Kevin | Done | INFRA-01 | - | Chore | infra,docker,setup
INFRA-03 | Infrastructure | Setup PostgreSQL database & schema migration | • PostgreSQL container running • Schema migration tool (Prisma/Sequelize) • ERD implemented | Must Have | 3 | Prep | Kevin+Dzaky | Done | INFRA-02 | - | Chore | infra,database,setup
INFRA-04 | Infrastructure | Setup Local STT model | • STT model selected (Whisper.cpp/Vosk) • Model downloaded & tested • API endpoint created | Must Have | 5 | Prep | Kevin | Done | INFRA-02 | - | Spike | infra,ai,stt,setup | TBD: Model choice
INFRA-05 | Infrastructure | Setup LLM API integration (Qwen via Open Router) | • Open Router account • Qwen 3.6 tested • API wrapper service created | Must Have | 3 | Prep | Kevin | Done | INFRA-02 | - | Chore | infra,ai,llm,setup
INFRA-06 | Infrastructure | Setup Vector DB (ChromaDB) | • ChromaDB installed • Connection tested • Basic CRUD working | Must Have | 3 | Prep | Kevin | Done | INFRA-02 | - | Chore | infra,ai,vectordb,setup | For CV/candidate semantic search
QA-08 | Testing & QA | AI accuracy testing (CV review, Interview eval, Career planner) | • CV review accuracy ≥80% • Interview eval accuracy ≥80% • Career planner relevance ≥80% • Test sample prompts | Must Have | 5 | Sprint 5 | Novian+Kevin | Planned | - | - | Testing | qa,ai,accuracy | Test AI output quality
QA-09 | Testing & QA | Integration testing (FE-BE-AI) end-to-end | • E2E test all user journeys • API integration tested • AI pipeline tested • Pass rate ≥95% | Must Have | 5 | Sprint 5 | Novian+Team | Planned | - | - | Testing | qa,integration,e2e | Test full user flows
QA-10 | Testing & QA | Performance testing (API response time & load) | • API response time ≤5s for AI calls • Page load time ≤3s • Load test 100 concurrent users | Must Have | 3 | Sprint 5 | Novian | Planned | - | - | Testing | qa,performance,load | Performance benchmarks
QA-11 | Testing & QA | Security testing (HTTPS, RBAC, SQL injection, XSS) | • HTTPS enabled • RBAC tested • SQL injection tested • XSS tested • Penetration test basic | Must Have | 5 | Sprint 5 | Johanes+Novian | Planned | - | - | Testing | qa,security,pentest | Security validation
QA-12 | Testing & QA | Stress testing (High load, concurrent users) | • Test 500+ concurrent users • Database load test • AI service load test • Identify bottlenecks | Should Have | 3 | Sprint 5 | Novian+Johanes | Planned | - | - | Testing | qa,stress,load | Optional if time permits
QA-13 | Testing & QA | Usability testing (User flow & UI/UX feedback) | • User flow tested • UI/UX feedback collected • Critical issues fixed • User acceptance | Should Have | 2 | Sprint 5 | Novian+Arrayyan | Planned | - | - | Testing | qa,usability,ux | User experience validation
DOC-01 | Documentation | API documentation (Swagger/OpenAPI) | • All endpoints documented • Request/response examples • Swagger UI available | Must Have | 3 | Sprint 5 | Kevin+Dzaky | Planned | - | - | Docs | docs,api,swagger
DOC-02 | Documentation | User manual (Candidate & Company) | • Step-by-step guide untuk candidate • Step-by-step guide untuk company • Screenshots included | Must Have | 5 | Sprint 5 | Johanes+Arrayyan | Planned | - | - | Docs | docs,manual,user
DOC-03 | Documentation | Deployment guide | • Environment setup guide • Deployment steps • Troubleshooting section | Must Have | 3 | Sprint 5 | Johanes | Planned | - | - | Docs | docs,deployment
DOC-04 | Documentation | Source code documentation | • Code comments • README per module • Architecture diagram | Must Have | 3 | Sprint 5 | Team | Planned | - | - | Docs | docs,code
DOC-05 | Documentation | Handover checklist & final report | • Handover checklist prepared • All deliverables listed • Sign-off template • Final project report | Must Have | 2 | Sprint 5 | Johanes | Planned | - | - | Docs | docs,handover

## Kanban WIP
KANBAN BOARD — Sprint Active (WIP Limit: 3 per person)
| Backlog |  |  | To Do | DESIGN |  | DEVELOPMENT |  |  |  | QA |  |  | DONE
| User Story | Sprint | Status |  | In Progress | Done | In Progress |  |  | Done
[7 empty] | Sebagai Company, saya ingin create job posting agar candidate dapat apply | Sprint 4 | US-007 |  |  | Sebagai Candidate, saya ingin career path recommendation agar tahu skill yang harus dipelajari | Sprint 3 | Sebagai Candidate, saya ingin register akun agar dapat akses platform | Sprint 1 |  | LEGENDA
[7 empty] | Sebagai Company, saya ingin add screening questions agar filter candidate | Sprint 4 | US-016 |  |  | Sebagai Candidate, saya ingin practice interview agar lebih siap | Sprint 3 | Sebagai Candidate, saya ingin login agar dapat gunakan fitur platform | Sprint 1 |  | NORMAL
[7 empty] | Sebagai Candidate, saya ingin apply ke job agar dapat melamar | Sprint 4 | US-005 |  |  | Sebagai System, saya harus auto-transcribe recording agar jawaban dapat dianalisis | Sprint 3 | Sebagai Company, saya ingin register akun agar dapat post lowongan | Sprint 1 |  | FIXED DATE
[7 empty] | Sebagai Candidate, saya ingin answer screening questions agar perusahaan evaluate | Sprint 4 | US-018,US-014 |  |  | Sebagai Candidate, saya ingin edit transcript agar kesalahan dapat diperbaiki | Sprint 3 | Sebagai Company, saya ingin login agar dapat manage lowongan | Sprint 1 |  | URGENT
[12 empty] | Sebagai Candidate, saya ingin AI evaluation agar tahu kualitas jawaban | Sprint 3
[14 empty] | Sebagai Candidate, saya ingin create & update profile agar recruiter lihat background | Sprint 2 | x
[14 empty] | Sebagai Candidate, saya ingin add experience, education, skills agar profile lengkap | Sprint 2
[14 empty] | Sebagai Company, saya ingin create company profile agar candidate tahu perusahaan | Sprint 2
[14 empty] | Sebagai Candidate, saya ingin upload CV agar AI analyze | Sprint 2
[14 empty] | Sebagai System, saya harus extract text dari CV agar AI process | Sprint 2
[14 empty] | Sebagai Candidate, saya ingin AI CV review agar tahu strengths & weaknesses | Sprint 2
⚠️ Kanban ini akan di-populate saat Sprint Planning. Sample cards di atas menunjukkan format yang digunakan.
WIP LIMIT: Max 3 tasks "In Progress" per person ¦ Update daily di standup ¦ Move cards left-to-right

## Definition of Done
DEFINITION OF DONE (DoD)
Level | Criteria
Task DoD | ☐ Code written & self-reviewed ☐ Unit test passed ☐ Peer code review done ☐ No linting errors ☐ Committed to Git
User Story DoD | ☐ All tasks DONE ☐ Acceptance criteria met ☐ Integration test passed ☐ UI/UX reviewed (if FE) ☐ API documented (if BE) ☐ Demo-able
Sprint DoD | ☐ All committed stories DONE ☐ Sprint review conducted ☐ Retrospective done ☐ Increment deployed to staging ☐ Sprint report submitted
MVP DoD | ☐ All MVP stories DONE ☐ E2E test passed ☐ Performance test passed (≤5s) ☐ Security test passed ☐ User docs complete ☐ Deployment guide complete ☐ Handover ready

## Milestone
WEEKLY MILESTONE — 19 MJ: AI Career Development & Hiring Platform
10 Minggu ¦ Target: 24 Mei (55h) atau 31 Mei (63h) ¦ Buffer: Sprint 5
Minggu | Periode | Sprint | Milestone | Deliverable | Kriteria Sukses | Owner | Status | Catatan | Progress
Minggu 1 | 30 Mar-5 Apr | Prep | Requirements DONE | • PRD/SKPL final • ERD finalized • API contract • Tech architecture • Docker setup • Wireframe | ✔ Requirements documented ✔ Tech stack decided ✔ Sprint 1 ready | Johanes+Team | Done | ⚠ Finalize STT model, Cloud storage, Deployment platform | 0%
Minggu 2-3 | 6-19 Apr | Sprint 1 | Auth & Profile DONE | • Register & Login (Candidate+Company) • Profile CRUD • Hi-fi design auth pages | ✔ User register with validation ✔ Login & session works ✔ Profile CRUD API works ✔ After login redirect (blank page OK) | Arrayyan+Kevin+Dzaky | Done | ⚠ Learning curve React/Express | 0%
Minggu 4-5 | 20 Apr-3 Mei | Sprint 2 | CV & AI Review DONE | • Upload CV • Extract text • AI CV Review • View results | ✔ CV upload works ✔ Text extraction ≥90% ✔ AI review shows feedback ✔ Response time ≤5s | Kevin+Dzaky+Arrayyan | On Progress | ⚠ LLM integration (Qwen via Open Router) ⚠ CV parsing accuracy | 0%
Minggu 6-7 | 4-17 Mei | Sprint 3 | Career+Interview DONE | • Career Planner • Interview record • STT transcribe • View transcript | ✔ Career planner relevant ✔ Recording works ✔ Transcription ≥85% ✔ Transcript visible | Kevin+Arrayyan+Dzaky | To Do | ⚠ Local STT setup (Whisper.cpp) ⚠ STT accuracy ⚠ Media storage size | 0%
Minggu 8-9 | 18-31 Mei | Sprint 4 | Edit+Eval+Job DONE | • Transcript editor • AI Interview Eval • Job posting • Job apply | ✔ Edit & save transcript ✔ AI eval score+feedback ✔ Company create job ✔ Candidate apply ✔ Target 55/63 hari | All Team | Planned | ⚠ CRITICAL: 55h target=24 Mei, 63h=31 Mei ⚠ Feature overload risk | 0%
Minggu 10 | 1-7 Jun | Sprint 5 | Integration+Testing DONE | • Screening • Dashboard • Recommendation • E2E test • Bug fix • Docs | ✔ Screening works ✔ Dashboard shows data ✔ E2E pass ≥95% ✔ Bugs resolved ✔ Docs complete | All Team | Planned | ⚠ BUFFER SPRINT ⚠ Focus: testing, bugs, docs | 0%
SUMMARY: 10 Weeks ¦ 5 Sprints+Prep ¦ Target: 55h (24 Mei) / 63h (31 Mei) ¦ Buffer: Sprint 5

## Catatan & Conventions
CATATAN, LEGEND & TBD ITEMS
LEGEND - Epic Colors
Epic | Color | Usage | Sprint
Auth & User Management |  | Register, Login (Candidate & Company) | Sprint 1
Candidate Profile |  | Profile CRUD, Experience, Skills | Sprint 1
CV Management |  | Upload CV, Extract Text, AI Review | Sprint 2
Career Planner |  | AI Career Path Recommendation | Sprint 2
Interview Practice |  | Record, Transcribe, Edit, AI Eval | Sprint 3
Job Management |  | Job Posting, Screening Questions | Sprint 4
Recruiter Dashboard |  | View Candidates, AI Scores, Recommendations | Sprint 5
TBD ITEMS (to be decided in Sprint Planning)
Item | Current Status | Decision Needed By | Owner
Local STT Model | TBD | Week 1 (Preparation) | Kevin
Cloud Storage | TBD | Week 1 (Preparation) | Johanes
Deployment Platform | TBD | Week 1 (Preparation) | Johanes